## Sheet1
Req. ID | Requirement Description | Jira Story ID | Design Ref (Wireframe/Flow) | Test Case ID | Status | Comments | Comments
FR-01 | User can register using name, mobile, and email | SCRUM-9 (UM-01) | WF-Register | TC-01 | Done | Covered in Sprint 1 | Covered in Sprint 1
FR-02 | User can log in with mobile and password | SCRUM-10 (UM-02) | WF-Login | TC-02 | Done | Tested and Passed | UAT Passed
FR-03 | User can reset forgotten password using OTP | SCRUM-11 (UM-03) | WF-ForgotPassword | TC-03 | Done | Validated in UAT | Dev pending approval
FR-04 | User can update profile details | SCRUM-12 (UM-04) | WF-ProfileEdit | TC-04 | Done | Included in Sprint 2 | Scheduled for Sprint 3
FR-05 | Patient can search for doctors by specialty/location | SCRUM-13 (AB-01) | WF-SearchDoctor | TC-05 | Done | Search functionality verified | Tested manually
FR-06 | Patient can view doctor availability | SCRUM-14 (AB-02) | WF-ViewAvailability | TC-06 | Done | Matches calendar logic
FR-07 | Patient can book an appointment | SCRUM-15 (AB-03) | WF-BookAppointment | TC-07 | Done | Tested in Sprint 2
FR-08 | Patient can cancel/reschedule appointments | SCRUM-16 (AB-04) | WF-CancelAppointment | TC-08 | Done | Works with status update
FR-09 | Patient can view upcoming appointments | SCRUM-17 (DB-01) | WF-PatientDashboard | TC-09 | Done | Tested in Sprint 3
FR-10 | Patient can view appointment history | SCRUM-18 (DB-02) | WF-HistoryView | TC-10 | Done | UAT completed
FR-11 | Doctor can view their daily appointments | SCRUM-19 (DB-03) | WF-DoctorDashboard | TC-11 | Done | Reviewed with SME
FR-12 | Users can view and edit profile info | SCRUM-20 (DB-04) | WF-ProfilePage | TC-12 | Done | Matches update rules
FR-13 | User receives booking confirmation | SCRUM-21 (NS-01) | - | TC-13 | Done | Email & SMS verified
FR-14 | User receives appointment reminder | SCRUM-22 (NS-02) | - | TC-14 | Done | Cron job simulation passed
FR-15 | Doctor notified when appointment is booked | SCRUM-23 (NS-03) | - | TC-15 | Done | Alert shown on dashboard
FR-16 | Notification on appointment cancellation | SCRUM-24 (NS-04) | - | TC-16 | Done | Auto-alert functional
FR-17 | Admin can add new doctors | SCRUM-25 (ADM-01) | WF-AddDoctor | TC-17 | Done | Added from admin panel
FR-18 | Admin can update doctor availability | SCRUM-26 (ADM-02) | WF-UpdateAvailability | TC-18 | Done | Tested by role access
FR-19 | Admin can remove doctor from listing | SCRUM-27 (ADM-03) | WF-RemoveDoctor | TC-19 | Done | Confirmed logic
FR-20 | Admin can view appointment logs | SCRUM-28 (ADM-04) | WF-AppointmentLogs | TC-20 | Done | Data exports verified
FR-21 | User can filter doctors by specialty | SCRUM-29 (SF-01) | WF-FilterSpecialty | TC-21 | Done | Dropdown filter working
FR-22 | User can filter doctors by location | SCRUM-30 (SF-02) | WF-FilterLocation | TC-22 | Done | Location logic accurate
FR-23 | User can filter by availability | SCRUM-31 (SF-03) | WF-FilterDate | TC-23 | Done | Calendar validation done
FR-24 | Patient can submit doctor feedback | SCRUM-32 (FB-01) | WF-FeedbackForm | TC-24 | Done | Star rating saved
FR-25 | Patient can view doctor ratings | SCRUM-33 (FB-02) | WF-ViewRatings | TC-25 | Done | Visible on profile
FR-26 | Users have role-based access control | SCRUM-34 (SEC-01) | WF-AccessControl | TC-26 | Done | Access verified
FR-27 | System enforces secure login/logout | SCRUM-35 (SEC-02) | WF-LoginFlow | TC-27 | Done | Session check passed
FR-28 | Session expires after inactivity | SCRUM-36 (SEC-03) | WF-SessionTimeout | TC-28 | Done | Auto logout working